## Cover
LOGO | Project Name: | ChacaLongHai | Designed by: | Nguyễn Minh Châu
| Module Name: |  | Designed date: | 2022-04-06
| Release Version: | 1 | Executed by:
Execution date:
REVISION HISTORY
Date | Version | Description | Author/Reviewer | Sprint
2022-04-13 | 1 | Manage User Function

## Environment
Device | Browser | Environment
Google Chrome

## Function
|  |  |  | Status Definition | Status
|  |  |  | Total of testcase | 57
|  |  |  | Total of untested testcase | 0
|  |  |  | Passed |  | Blocked | 0
|  |  |  | Failed | 0 | Not Executed | 57
Test Case ID | Sprint | Purpose |  | Precondition | Precondition Details | Steps | Step Details / Test Data | Expected Results | Actual Result |  | Comment
Case for UI
c1 | 2 | Test the interfaces of the manage user function |  | Login successfully | - Having stable internet connection | Open the manage user screen | - Access to the link: "https://chacalonghai.vn/" - Input email = "admin@gmail.com" - Input password: 123456 | "- Similar to the requirement designs '- Screen shows informations: + The list of users + Button"Add". '- The same length , width of labels, icon, textbox '- Layout will not be crack when resizing and rotating the screen" |  | Passed
c2 | [5 empty] | Test display Logo of software |  | The screen displays based on the design |  | Passed
c3 | [5 empty] | Test display Sidebar menu |  |  |  | Passed
c5 | [5 empty] | Test display text "Danh sách người dùng" |  |  |  | Passed
c6 | [5 empty] | Test display button [Add] |  |  |  | Passed
c9 | [5 empty] | Test display column [The order] |  |  |  | Passed
c10 | [5 empty] | Test display column [Avatar of user] |  |  |  | Passed
c11 | [5 empty] | Test display column [User's name] |  |  |  | Passed
c12 | [5 empty] | Test display column [Email] |  |  |  | Passed
c13 | [5 empty] | Test display column [Created Date] |  |  |  | Passed
c14 | [5 empty] | Test display column [Status] |  |  |  | Passed
c15 | [5 empty] | Test display column [Promotional price] |  |  |  | Passed
c16 | [5 empty] | Test display column [Position] |  |  |  | Passed
c17 | [5 empty] | Test display column [userhot] |  |  |  | Passed
c18 | [5 empty] | Test display column [Status] |  |  |  | Passed
c19 | [5 empty] | Test display column [Funcion] |  |  |  | Passed
c20 | [5 empty] | Test display icon [Edit] |  |  |  | Passed
c21 | [5 empty] | Test display icon [Delete] |  |  |  | Passed
c22 |  | Test the interface in modal [Add new product] |  | - Click button [Add product] |  | Test display textbox [Product's Name] |  |  |  | Passed
c23 | [5 empty] | Test display textbox [Product's Image] |  | - Display button [Choose file] |  | Passed
c24 | [5 empty] | Test display textbox [Quantity in stock] |  | The screen displays based on the design |  | Passed
c25 | [5 empty] | Test display textbox [Cost] |  |  |  | Passed
c26 | [5 empty] | Test display textbox [Promotional price] |  |  |  | Passed
c27 | [5 empty] | Test display combobox [userCategory] |  |  |  | Passed
c28 | [5 empty] | Test display textbox [Position] |  |  |  | Passed
c29 | [5 empty] | Test display checkbox [Status] |  |  |  | Passed
c30 | [5 empty] | Test display icon [Create] |  |  |  | Passed
c31 |  | Tab button |  | Check when press Tab button |  | Press constantly Tab button |  | '- Mouse moves from at the top to the bottom, from the left to the right. |  | Passed
c32 |  | Test the whole UI on the screeen |  | - Access to the link: "https://chacalonghai.vn/" |  | - Test the layout, font, word's color - Check the spell of word are correct or not |  | 1. Layout '- Labels, edit text, button are arranged equally, not be skew '- Forms are arrange suitably and easy to use 2. Font, color's word - Labels and font must be the same color and size |  | Passed
Case for functions
c1 | 2 | Check modal [Add new product] | Check field [Product's name] is required | Click button [Add product] | '- Access successfully to the e-commerce website | - Input and delete data - Click mouse outside the textbox - Click button Create |  | Display an error message:"You need input the Product's Name" |  | Passed
c2 |  |  | Check field [Product's name] when input special characters and number |  |  | - Input Product's name equal to special characters | - Enter [Product's Name] = "@#@$" | Can not create new product |  | Passed
c3 |  |  | Check field [Product's name] when Copy/Paste special characters and number |  |  | - Copy/Paste Product's name equal to special characters | - Copy/Paste [Product's Name] = "@#@$" | Can not create new product |  | Failed
c4 |  |  | Check function [Choose file] |  |  | Click on button Choose file | Choose one file in the computer | The field is selected, display on the image of product |  | Passed
c5 |  |  | Check textbox [ Quantity in stock] is the words and special characters |  |  | - Input [Quantity in stock] equal to special characters and words | - Enter [Quantity in stock] = "abc@#@$" | Can not create new product |  | Passed
c7 | [5 empty] | - Copy/Paste [Quantity in stock] equal to special characters and words | - Copy/Paste [Quantity in stock] = "abc@#@$" | Can not create new product |  | Passed
c8 |  |  | Check textbox [ Cost] is the words and special characters |  |  | - Input [Cost] equal to special characters and words | - Enter [Cost] = "abc@#@$" | Can not create new product |  | Passed
[6 empty] | - Copy/Paste [Cost] equal to special characters and words | - Copy/Paste [Cost] = "abc@#@$" | Can not create new product |  | Passed
|  |  | Check textbox [Promotional price] is the words and special characters |  |  | - Input [Promotional price] equal to special characters and words | - Enter [Promotional price] = "abc@#@$" | Can not create new product |  | Passed
c9 | [5 empty] | - Copy/Paste [Promotional price] equal to special characters and words | - Copy/Paste [Promotional price] = "abc@#@$" | Can not create new product |  | Passed
c10 |  |  | Check textbox [Promotional price] is greater than [Cost] |  |  | Input [Promotional price] is greater than [Cost] | '- Input [Cost] = 230.000 vnđ - Input [Promotional price] = 300.000 vnd |  |  | Failed
c12 |  |  | Check combobox [Category of Product] |  |  | Click on the combobox [Category of product] |  | The combobox display all the category |  | Passed
c13 |  |  | Check textbox [Position] when enter words and special characters |  |  | - Input [Position] equal to special characters and words | - Enter [Position] = "abc@#@$" | Display an error message: "Please enter a number" |  | Passed
c14 | [5 empty] | - Copy/Paste [Position] equal to special characters and words | - Copy/Paste [Position] = "abc@#@$" |  |  | Passed
c15 |  |  | Check action of textbox [Description] |  |  | - Enter a new description - Change the font and color of text - Click button [Create] | - Input [Description] = " Sản phẩm đến từ Vũng tàu" | - Add a new product successfully - Direct to screen list of product |  | Passed
c16 |  |  | Check the action of button [Create] |  |  | - Create a new product - Click button [Create] - Check the action after | - Input [Product Name] = "Hambuger" - Input [Cost] = "40.000" - Input [Quantity] = "120" - Choose [Position] = " Sản phẩm khác" - Click button [Create] |  |  | Passed
c17 |  | Check modal [Edit product] | Change randomly a field | Click icon [Edit] |  | - Choose randomly a product - Click icon edit - Chage a field - Click button [Update] | - Alter [Product Name] = "Hambuger" to "Chicken" - Click button [Update ] | Chage the information of that usersucessfully |  | Passed
c19 |  |  | Change randomly more than a field |  |  | - Choose randomly a product - Click icon edit - Chage more than a field - Click button [Update] |  | Chage the information of that usersucessfully |  | Passed
c20 |  |  | Chage all the information of product |  |  | - Choose randomly a product - Click icon edit - Chage all the info - Click button [Update] |  | Chage the information of that usersucessfully |  | Passed
c21 |  | Delete randomly a product |  | Click icon [Delete] |  | - Select a product - Click button [Delete] |  | - Display dialog confirm: "Are you sure want to delete?" |  | Passed
c22 | [5 empty] | - Click button [Yes] |  | - Delete successfully - Infor of usercan not display on the list |  | Passed
c24 |  | Cancel to delete randomly a product |  |  |  | - Select a product - Click button [Delete] |  | - Display dialog confirm: "Are you sure want to delete?" |  | Passed
c25 | [5 empty] | - Click button [No] |  | - Delete unsuccessfully - Infor of userstill display on the list |  | Passed